## Slide 1: CM4 Only
New area on Moodle for Construction Management IT
Enrolment key is ‘547kvr957’

## Slide 2: Basic Project Scheduling Time-Chainage Charts
Project Management
Year 4
Ref: Cooke B and Williams P (2009) Construction Planning, Programming & Control, Third Edition, Wiley-Blackwell Publishing, ISBN 978-1-4051-8380-2

## Slide 3: Time-Chainage Charts
AKA
  Time-Distance diagrams (or charts)
  Time-Location diagrams (or charts)
  Location-Time diagrams (or charts)
  Etc.
Time-chainage diagrams are a combination of the bar-chart and line of balance schedules.

## Slide 4: History
Relatively new tool for scheduling projects
TC charts have gained wide acceptance in:
  Motorway construction
  Railway construction
  Pipeline work
  Tunnel construction
  Bridges
The technique was used for tunnelling and fixed equipment installation on the channel tunnel project

## Slide 5
Time-chainage diagrams are only appropriate for certain types of project, and therefore is not as widely used as bar charts (Gantt) or network techniques.
  It is not available on MS Project…
Time chainage has distinct attributes and advantages on projects where it is important to depict
  The order of activities or operations
  The location of activities
  How activites must progress in relation to direction and distance
  Time, Key dates, holidays, etc.

## Slide 6
Chainage (Distance)
5
10
15
20
25
30
35
0
500
3500
1000
1500
2000
2500
3000
Weeks
Set Up Site
Holidays
Footbridge
Fencing
Bulk Earthworks
Road Surfacing
Drainage
Retaining
Wall

## Slide 7: Example
Consider a project to improve a 3.5km stretch of motorway. The activities are as follows
    Fencing
    Drainage
    Bulk Earthworks -
    Footbridge
    Retaining wall
    Road surfacing
Ref: Cooke B and Williams P (2009) Construction Planning, Programming & Control, Third Edition, Wiley-Blackwell Publishing, ISBN 978-1-4051-8380-2

## Slide 8
Further information
  Set-up Site
    starts at time 0,
    duration 6 weeks
  Fencing
    Starts week 7
    Duration 9 weeks, therefore finish week 15
    Full 3.5 km to be fenced
  Holiday Period
    Starts week 26 for 1 week
Ref: Cooke B and Williams P (2009) Construction Planning, Programming & Control, Third Edition, Wiley-Blackwell Publishing, ISBN 978-1-4051-8380-2

## Slide 9
5
10
15
20
25
30
35
0
500
3500
1000
1500
2000
2500
3000
Weeks
Chainage (Distance)
Set Up Site
Holidays
Fencing

## Slide 10
Further information
  Drainage
    starts week 12
    duration 4 weeks, therefore finish week 16
    Drainage required for full 3.5km
  Bulk Earthworks
    Starts week 15
    Duration 5 weeks, therefore finish week 20
    Required from 500m to 1000m
  Footbridge
    Starts week 16 for 9 weeks, therefore finish week 25
    Required 1500m
Ref: Cooke B and Williams P (2009) Construction Planning, Programming & Control, Third Edition, Wiley-Blackwell Publishing, ISBN 978-1-4051-8380-2

## Slide 11
5
10
15
20
25
30
35
0
500
3500
1000
1500
2000
2500
3000
Weeks
Chainage (Distance)
Set Up Site
Holidays
Footbridge
Fencing
Bulk Earthworks
Drainage

## Slide 12
Further information
  Retaining Wall
    starts week 16
    duration 8 weeks, therefore finish week 24
    Required from 2500m to 2900m
    Progresses at a rate of 50m per week
  Road Surfacing
    Starts week 30
    Duration 5 weeks, therefore finish week 35
    Entire 3.5km to be surfaced
Ref: Cooke B and Williams P (2009) Construction Planning, Programming & Control, Third Edition, Wiley-Blackwell Publishing, ISBN 978-1-4051-8380-2

## Slide 13
5
10
15
20
25
30
35
0
500
3500
1000
1500
2000
2500
3000
Weeks
Chainage (Distance)
Set Up Site
Holidays
Footbridge
Fencing
Bulk Earthworks
Road Surfacing
Drainage
Retaining
Wall

## Slide 14: Tips for Constructing Time Chainage Diagrams
  Examine Layout Drawings etc and determine locations of important features
  Draw a sketch of the diagram, and include holidays etc.
  List main activities in approximate sequence. Include site setup and clearance
  For static activities (footbridge), ‘block out’ the location, distance, and the correct duration
  Beware of changes in axis: time chainage is relatively new and conventions have yet to take hold

## Slide 15
5
10
15
20
25
30
35
0
500
3500
1000
1500
2000
2500
3000
Weeks
Chainage (Distance)
Set Up Site
Holidays
Footbridge
Fencing
Bulk Earthworks
Road Surfacing
Drainage
Retaining
Wall

## Slide 16
5
10
15
20
25
30
35
0
500
3500
1000
1500
2000
2500
3000
Weeks
Chainage (Distance)
Set Up Site
Holidays
Footbridge
Fencing
Bulk Earthworks
Road Surfacing
Drainage
Retaining
Wall

## Slide 17: TILOS
Commercial Software Package for Time Chainage Diagrams
Free demo version available on website
  http://www.astadev.com/software/tilos/index.asp
Installed in 4C02 and 4C03

## Slide 19: TILOS Example

## Slide 20: Further Reading
Cooke B. and Williams P. (2009) Construction Planning, Programming & Control, Third Edition, Wiley-Blackwell Publishing, Chapter 9
ISBN 978-1-4051-8380-2