## Slide 1: Project Time Management (Cont.)
Project Management
Year 4

## Slide 2: Fast Tracking
Fast-Tracking: commencing phases (or activities) before their logical predecessor is completed.
Increases Risk
  Can result in having to re-work elements of the project, which may result in a net gain of zero time.
Fast Tracking carries many of the risks and trade-offs associated with Crashing.
Fast Tracking will also have costs associated. Analysis can be carried out in a similar manner to Crash Costing.

## Slide 3: What-If Scenario Analysis
Can be useful for gaining a better understanding of the project schedule
  What if activity B is extended by 3 weeks
  What if the start of activity E is delayed by 1 week
  Etc.
Significant ‘What If’ questions should be posed (and recorded) as part of Risk Analysis
What-If questions need to be realistic
  Year 2000 contingency plan for a factory
    Enough Fuel held on site to run electricity generators for 3 months.
    Question ‘What if the ESB is not generating again after that time’
    It won’t matter….

## Slide 4: Resource Levelling
Remember:

## Slide 5: Resource Levelling
Resource Levelling involves changing the project program to ensure that
  Resources are not over allocated, and only used when available
  The logic of the project is maintained
In the ‘Bob & Jim’ example no logic is stated in the Gantt Chart.
  One of the limitations of Gantt Charts
So, to level the resources we move tasks to suit resource availability

## Slide 6: Resource Levelled Gantt Chart
This example is not particularly efficient
  Bob is not used on Day 1
  There is no indication that Tasks D and F can be moved in this manner. (no network logic)

## Slide 7: Schedule Development
Part of the Planning Process Group

## Slide 8: Schedule Development
Tools & Techniques (cont.)
  Project Management Software
    Primavera, MS Project, etc.
  Applying Calendars
    Project Calendars: Identification of working time and non-working time
    Resource Calendars: Identification of resource availability (holidays, shift workers, resource utilised elsewhere, etc.)
  Adjusting Leads and Lags
  Schedule Model
    Compilation of Schedule Data and Information used to generate the schedule.
    Typically used for reference later on during the project

## Slide 9: Schedule Development
Outputs
  Project Schedule
    Network Diagrams
    Bar Charts (Gantt)
    Milestone charts
  Schedule Model Data
    Supporting Data
  Schedule Baseline
  Resource Requirements
  Activity Attributes (Updates)
  Project Calendar (Updates)
  Requested Changes
  Project Management Plan (Updates)
    Schedule Management Plan (Updates)

## Slide 10: Control Schedule
Part of the Monitoring & Controlling Process Group

## Slide 11: Control Schedule
Schedule Control is concerned with
  Determining the current status of the project schedule
  Influencing the factors that create schedule changes
  Determining that the project schedule has changed
  Managing the actual changes as they occur

## Slide 12: Control Schedule
Inputs
  Project Management Plan
    Schedule Management Plan is part of overall Project Management Plan
    States how the Schedule will be managed and controlled
      Version number, circulation, processes, etc.
  Project Schedule
    Initial Approved Project Schedule
    Controlled Updated version of Approved Project Schedule
    Used as a yardstick against which project progress and performance is measured

## Slide 13: Control Schedule
Inputs
  Work Performance Information
    Performance Reports
    Contain Information on schedule performance
      Planned v. Actual start dates, completion dates, milestones, etc. (Ms Project View|Table:Tracking)
    Also highlight potential issues before they arise
      ‘look-aheads’
  Organisational Process Assets

## Slide 14: Control Schedule
Tools & Techniques
  Progress Reports
    Information on actual start and finish dates, rates of progress,
    Potential issues arising (unforeseen ground conditions)
    Earned Value
  Schedule Change Control System
    Details the processes that need to be undertaken to modify the project schedule.
      Tracking Systems, Approvals, etc.
    Part of the Integrated Change Control Process

## Slide 15: Control Schedule
Tools & Techniques
  Performance Measurement
    Schedule Variance (SV) and Schedule Performance Index (SPI); used to assess the magnitude of project schedule variations; all part of Earned Value Management System
  Project Management Software
    MS Project, et al
  Variance Analysis
    Comparison of target dates with actual and forecast dates
    Identification of trends and magnitudes of variances

## Slide 16: Control Schedule
Tools & Techniques
  Schedule Comparison Bar Charts
    e.g. MS Project %age completion

## Slide 17: Control Schedule
Outputs
  Work Performance Measurements
    EVMS Information
  Organisational Process Assets Updates
    Causes of Variances
    Corrective Actions chosen and reason for
    Lessons Learned
  Change Requests
    Processed through Integrated Change Control

## Slide 18: Control Schedule
Outputs
  Project Management Plan Updates
    Project Baseline Updates
    Cost Baseline Updates
    Schedule Management Plan Updates
  Project Document Updates
    Schedule Data
    Project Schedule

## Slide 19
Next Lecture
  Reading: ‘A Guide to the Project Management Body of Knowledge’ Chapter 7
    Cost Estimating
    Cost Budgeting
    Cost Control