## Inflation Index
Consumer Price Index |  |  | Wholesale Construction |  |  | Construction Labour
2000M01 | 90.4 | 0% | 2000M01 | 97 | 0%
2000M02 | 91.2 | 0.885% | 2000M02 | 97.8 | 0.8247%
2000M03 | 91.8 | 1.549% | 2000M03 | 98.2 | 1.237%
2000M04 | 92.5 | 2.323% | 2000M04 | 99 | 2.062%
2000M05 | 93.1 | 2.987% | 2000M05 | 99.6 | 2.68%
2000M06 | 93.7 | 3.65% | 2000M06 | 100 | 3.093% | 2000 | 13.97 |  | 0%
2000M07 | 94 | 3.982% | 2000M07 | 100.1 | 3.196% |  |  | 1 | 0.7516%
2000M08 | 94.5 | 4.535% | 2000M08 | 100.5 | 3.608% |  |  | 2 | 1.503%
2000M09 | 94.9 | 4.978% | 2000M09 | 101.3 | 4.433% |  |  | 3 | 2.255%
2000M10 | 95.5 | 5.642% | 2000M10 | 102 | 5.155% |  |  | 4 | 3.006%
2000M11 | 95.9 | 6.084% | 2000M11 | 102.2 | 5.361% |  |  | 5 | 3.758%
2000M12 | 95.9 | 6.084% | 2000M12 | 102.3 | 5.464% |  |  | 6 | 4.51%
2001M01 | 95.1 | 5.199% | 2001M01 | 103 | 6.186% |  |  | 7 | 5.261%
2001M02 | 96 | 6.195% | 2001M02 | 103.8 | 7.01% |  |  | 8 | 6.013%
2001M03 | 96.8 | 7.08% | 2001M03 | 104 | 7.216% |  |  | 9 | 6.764%
2001M04 | 97.6 | 7.965% | 2001M04 | 104.6 | 7.835% |  |  | 10 | 7.516%
2001M05 | 98.2 | 8.628% | 2001M05 | 104.6 | 7.835% |  |  | 11 | 8.268%
2001M06 | 98.7 | 9.181% | 2001M06 | 104.9 | 8.144% | 2001 | 15.23 |  | 9.019%
2001M07 | 98.5 | 8.96% | 2001M07 | 105.2 | 8.454% |  |  | 1 | 10.1%
2001M08 | 98.8 | 9.292% | 2001M08 | 105.6 | 8.866% |  |  | 2 | 11.19%
2001M09 | 99.2 | 9.735% | 2001M09 | 105.7 | 8.969% |  |  | 3 | 12.28%
2001M10 | 99.6 | 10.18% | 2001M10 | 106.2 | 9.485% |  |  | 4 | 13.36%
2001M11 | 99.5 | 10.07% | 2001M11 | 106 | 9.278% |  |  | 5 | 14.45%
2001M12 | 100 | 10.62% | 2001M12 | 105.9 | 9.175% |  |  | 6 | 15.53%
2002M01 | 99.8 | 10.4% | 2002M01 | 106.6 | 9.897% |  |  | 7 | 16.62%
2002M02 | 100.5 | 11.17% | 2002M02 | 107.2 | 10.52% |  |  | 8 | 17.7%
2002M03 | 101.4 | 12.17% | 2002M03 | 107.2 | 10.52% |  |  | 9 | 18.79%
2002M04 | 102.3 | 13.16% | 2002M04 | 107.6 | 10.93% |  |  | 10 | 19.88%
2002M05 | 102.8 | 13.72% | 2002M05 | 107.8 | 11.13% |  |  | 11 | 20.96%
2002M06 | 103 | 13.94% | 2002M06 | 107.9 | 11.24% | 2002 | 17.05 |  | 22.05%
2002M07 | 102.6 | 13.5% | 2002M07 | 107.9 | 11.24% |  |  | 1 | 22.54%
2002M08 | 103.2 | 14.16% | 2002M08 | 108.1 | 11.44% |  |  | 2 | 23.03%
2002M09 | 103.7 | 14.71% | 2002M09 | 108.4 | 11.75% |  |  | 3 | 23.51%
2002M10 | 104.2 | 15.27% | 2002M10 | 109.1 | 12.47% |  |  | 4 | 24%
2002M11 | 104.3 | 15.38% | 2002M11 | 109 | 12.37% |  |  | 5 | 24.49%
2002M12 | 105 | 16.15% | 2002M12 | 109.1 | 12.47% |  |  | 6 | 24.98%
2003M01 | 104.6 | 15.71% | 2003M01 | 107.9 | 11.24% |  |  | 7 | 25.47%
2003M02 | 105.6 | 16.81% | 2003M02 | 108.3 | 11.65% |  |  | 8 | 25.96%
2003M03 | 106.4 | 17.7% | 2003M03 | 108.6 | 11.96% |  |  | 9 | 26.45%
2003M04 | 106.7 | 18.03% | 2003M04 | 108.6 | 11.96% |  |  | 10 | 26.94%
2003M05 | 106.6 | 17.92% | 2003M05 | 108.6 | 11.96% |  |  | 11 | 27.43%
2003M06 | 106.6 | 17.92% | 2003M06 | 108.4 | 11.75% | 2003 | 17.87 |  | 27.92%
2003M07 | 105.8 | 17.04% | 2003M07 | 108.5 | 11.86% |  |  | 1 | 28.36%
2003M08 | 106.5 | 17.81% | 2003M08 | 108.7 | 12.06% |  |  | 2 | 28.81%
2003M09 | 106.7 | 18.03% | 2003M09 | 108.7 | 12.06% |  |  | 3 | 29.26%
2003M10 | 106.6 | 17.92% | 2003M10 | 109.3 | 12.68% |  |  | 4 | 29.71%
2003M11 | 106.6 | 17.92% | 2003M11 | 109.7 | 13.09% |  |  | 5 | 30.15%
2003M12 | 107 | 18.36% | 2003M12 | 109.8 | 13.2% |  |  | 6 | 30.6%
2004M01 | 106.5 | 17.81% | 2004M01 | 110.2 | 13.61% |  |  | 7 | 31.05%
2004M02 | 107.4 | 18.81% | 2004M02 | 112.2 | 15.67% |  |  | 8 | 31.5%
2004M03 | 107.8 | 19.25% | 2004M03 | 114.6 | 18.14% |  |  | 9 | 31.94%
2004M04 | 108.2 | 19.69% | 2004M04 | 116.5 | 20.1% |  |  | 10 | 32.39%
2004M05 | 108.4 | 19.91% | 2004M05 | 117.9 | 21.55% |  |  | 11 | 32.84%
2004M06 | 109 | 20.58% | 2004M06 | 118.5 | 22.16% | 2004 | 18.62 |  | 33.29%
2004M07 | 108.7 | 20.24% | 2004M07 | 119.3 | 22.99% |  |  | 1 | 34.07%
2004M08 | 109.3 | 20.91% | 2004M08 | 120.1 | 23.81% |  |  | 2 | 34.86%
2004M09 | 109.4 | 21.02% | 2004M09 | 121 | 24.74% |  |  | 3 | 35.65%
2004M10 | 109.5 | 21.13% | 2004M10 | 121.6 | 25.36% |  |  | 4 | 36.44%
2004M11 | 109.7 | 21.35% | 2004M11 | 122.5 | 26.29% |  |  | 5 | 37.22%
2004M12 | 109.8 | 21.46% | 2004M12 | 123.5 | 27.32% |  |  | 6 | 38.01%
2005M01 | 108.9 | 20.46% | 2005M01 | 123.2 | 27.01% |  |  | 7 | 38.8%
2005M02 | 109.8 | 21.46% | 2005M02 | 123 | 26.8% |  |  | 8 | 39.58%
2005M03 | 110.1 | 21.79% | 2005M03 | 122.7 | 26.49% |  |  | 9 | 40.37%
2005M04 | 110.6 | 22.35% | 2005M04 | 123 | 26.8% |  |  | 10 | 41.16%
2005M05 | 111 | 22.79% | 2005M05 | 123.4 | 27.22% |  |  | 11 | 41.95%
2005M06 | 111.3 | 23.12% | 2005M06 | 123.7 | 27.53% | 2005 | 19.94 |  | 42.73%
2005M07 | 111.3 | 23.12% | 2005M07 | 124 | 27.84% |  |  | 1 | 42.79%
2005M08 | 111.8 | 23.67% | 2005M08 | 124 | 27.84% |  |  | 2 | 42.84%
2005M09 | 112.7 | 24.67% | 2005M09 | 124.4 | 28.25% |  |  | 3 | 42.9%
2005M10 | 112.8 | 24.78% | 2005M10 | 125.6 | 29.48% |  |  | 4 | 42.95%
2005M11 | 112.6 | 24.56% | 2005M11 | 126.5 | 30.41% |  |  | 5 | 43%
2005M12 | 112.5 | 24.45% | 2005M12 | 126.7 | 30.62% |  |  | 6 | 43.06%
2006M01 | 112.2 | 24.12% | 2006M01 | 127.7 | 31.65% |  |  | 7 | 43.11%
2006M02 | 113.4 | 25.44% | 2006M02 | 129.4 | 33.4% |  |  | 8 | 43.16%
2006M03 | 113.9 | 26% | 2006M03 | 131 | 35.05% |  |  | 9 | 43.22%
2006M04 | 114.8 | 26.99% | 2006M04 | 133 | 37.11% |  |  | 10 | 43.27%
2006M05 | 115.3 | 27.54% | 2006M05 | 134.7 | 38.87% |  |  | 11 | 43.32%
2006M06 | 115.6 | 27.88% | 2006M06 | 134.6 | 38.76% | 2006 | 20.03 |  | 43.38%
2006M07 | 116 | 28.32% | 2006M07 | 135.1 | 39.28% |  |  | 1 | 43.83%
2006M08 | 116.8 | 29.2% | 2006M08 | 136.2 | 40.41% |  |  | 2 | 44.29%
2006M09 | 117.2 | 29.65% | 2006M09 | 136.7 | 40.93% |  |  | 3 | 44.74%
2006M10 | 117.2 | 29.65% | 2006M10 | 138.2 | 42.47% |  |  | 4 | 45.19%
2006M11 | 117.6 | 30.09% | 2006M11 | 138.6 | 42.89% |  |  | 5 | 45.65%
2006M12 | 118 | 30.53% | 2006M12 | 138.8 | 43.09% |  |  | 6 | 46.1%
2007M01 | 117.9 | 30.42% | 2007M01 | 139 | 43.3% |  |  | 7 | 46.55%
2007M02 | 118.9 | 31.53% | 2007M02 | 139.1 | 43.4% |  |  | 8 | 47.01%
2007M03 | 119.7 | 32.41% | 2007M03 | 140.2 | 44.54% |  |  | 9 | 47.46%
2007M04 | 120.6 | 33.41% | 2007M04 | 141.3 | 45.67% |  |  | 10 | 47.91%
2007M05 | 121.1 | 33.96% | 2007M05 | 141.5 | 45.88% |  |  | 11 | 48.37%
2007M06 | 121.4 | 34.29% | 2007M06 | 141.9 | 46.29% | 2007 | 20.79 |  | 48.82%
2007M07 | 121.7 | 34.62% | 2007M07 | 142.5 | 46.91%
2007M08 | 122.2 | 35.18% | 2007M08 | 142.4 | 46.8%
2007M09 | 122.7 | 35.73% | 2007M09 | 142.6 | 47.01%
2007M10 | 122.8 | 35.84% | 2007M10 | 142.7 | 47.11%

## Inflation Example
Consumer Price Index |  |  | Wholesale Construction |  |  | Construction Labour
2003M06 | 106.6 | #REF! | 2003M06 | 108.4 | #REF! | 2003 | 17.87 |  | 0%
2003M07 | 105.8 | #REF! | 2003M07 | 108.5 | #REF! |  |  | 1 | 0.3497%
2003M08 | 106.5 | #REF! | 2003M08 | 108.7 | #REF! |  |  | 2 | 0.6995%
2003M09 | 106.7 | #REF! | 2003M09 | 108.7 | #REF! |  |  | 3 | 1.049%
2003M10 | 106.6 | #REF! | 2003M10 | 109.3 | #REF! |  |  | 4 | 1.399%
2003M11 | 106.6 | #REF! | 2003M11 | 109.7 | #REF! |  |  | 5 | 1.749%
2003M12 | 107 | #REF! | 2003M12 | 109.8 | #REF! |  |  | 6 | 2.098%
2004M01 | 106.5 | 0% | 2004M01 | 110.2 | 0% |  |  | 7 | 2.448%
2004M02 | 107.4 | 0.8451% | 2004M02 | 112.2 | 1.815% |  |  | 8 | 2.798%
2004M03 | 107.8 | 1.221% | 2004M03 | 114.6 | 3.993% |  |  | 9 | 3.148%
2004M04 | 108.2 | 1.596% | 2004M04 | 116.5 | 5.717% |  |  | 10 | 3.497%
2004M05 | 108.4 | 1.784% | 2004M05 | 117.9 | 6.987% |  |  | 11 | 3.847%
2004M06 | 109 | 2.347% | 2004M06 | 118.5 | 7.532% | 2004 | 18.62 |  | 4.197%
2004M07 | 108.7 | 2.066% | 2004M07 | 119.3 | 8.258% |  |  | 1 | 4.813%
2004M08 | 109.3 | 2.629% | 2004M08 | 120.1 | 8.984% |  |  | 2 | 5.428%
2004M09 | 109.4 | 2.723% | 2004M09 | 121 | 9.8% |  |  | 3 | 6.044%
2004M10 | 109.5 | 2.817% | 2004M10 | 121.6 | 10.34% |  |  | 4 | 6.659%
2004M11 | 109.7 | 3.005% | 2004M11 | 122.5 | 11.16% |  |  | 5 | 7.275%
2004M12 | 109.8 | 3.099% | 2004M12 | 123.5 | 12.07% |  |  | 6 | 7.89%
2005M01 | 108.9 | 2.254% | 2005M01 | 123.2 | 11.8% |  |  | 7 | 8.506%
2005M02 | 109.8 | 3.099% | 2005M02 | 123 | 11.62% |  |  | 8 | 9.121%
2005M03 | 110.1 | 3.38% | 2005M03 | 122.7 | 11.34% |  |  | 9 | 9.737%
2005M04 | 110.6 | 3.85% | 2005M04 | 123 | 11.62% |  |  | 10 | 10.35%
2005M05 | 111 | 4.225% | 2005M05 | 123.4 | 11.98% |  |  | 11 | 10.97%
2005M06 | 111.3 | 4.507% | 2005M06 | 123.7 | 12.25% | 2005 | 19.94 |  | 11.58%
2005M07 | 111.3 | 4.507% | 2005M07 | 124 | 12.52% |  |  | 1 | 11.63%
2005M08 | 111.8 | 4.977% | 2005M08 | 124 | 12.52% |  |  | 2 | 11.67%
2005M09 | 112.7 | 5.822% | 2005M09 | 124.4 | 12.89% |  |  | 3 | 11.71%
2005M10 | 112.8 | 5.915% | 2005M10 | 125.6 | 13.97% |  |  | 4 | 11.75%
2005M11 | 112.6 | 5.728% | 2005M11 | 126.5 | 14.79% |  |  | 5 | 11.79%
2005M12 | 112.5 | 5.634% | 2005M12 | 126.7 | 14.97% |  |  | 6 | 11.84%
2006M01 | 112.2 | 5.352% | 2006M01 | 127.7 | 15.88% |  |  | 7 | 11.88%
2006M02 | 113.4 | 6.479% | 2006M02 | 129.4 | 17.42% |  |  | 8 | 11.92%
2006M03 | 113.9 | 6.948% | 2006M03 | 131 | 18.87% |  |  | 9 | 11.96%
2006M04 | 114.8 | 7.793% | 2006M04 | 133 | 20.69% |  |  | 10 | 12%
2006M05 | 115.3 | 8.263% | 2006M05 | 134.7 | 22.23% |  |  | 11 | 12.05%
2006M06 | 115.6 | 8.545% | 2006M06 | 134.6 | 22.14% | 2006 | 20.03 |  | 12.09%
2006M07 | 116 | 8.92% | 2006M07 | 135.1 | 22.6% |  |  | 1 | 12.44%
2006M08 | 116.8 | 9.671% | 2006M08 | 136.2 | 23.59% |  |  | 2 | 12.8%
2006M09 | 117.2 | 10.05% | 2006M09 | 136.7 | 24.05% |  |  | 3 | 13.15%
2006M10 | 117.2 | 10.05% | 2006M10 | 138.2 | 25.41% |  |  | 4 | 13.5%
2006M11 | 117.6 | 10.42% | 2006M11 | 138.6 | 25.77% |  |  | 5 | 13.86%
2006M12 | 118 | 10.8% | 2006M12 | 138.8 | 25.95% |  |  | 6 | 14.21%
2007M01 | 117.9 | 10.7% | 2007M01 | 139 | 26.13% |  |  | 7 | 14.57%
2007M02 | 118.9 | 11.64% | 2007M02 | 139.1 | 26.23% |  |  | 8 | 14.92%
2007M03 | 119.7 | 12.39% | 2007M03 | 140.2 | 27.22% |  |  | 9 | 15.28%
2007M04 | 120.6 | 13.24% | 2007M04 | 141.3 | 28.22% |  |  | 10 | 15.63%
2007M05 | 121.1 | 13.71% | 2007M05 | 141.5 | 28.4% |  |  | 11 | 15.99%
2007M06 | 121.4 | 13.99% | 2007M06 | 141.9 | 28.77% | 2007 | 20.79 |  | 16.34%
2007M07 | 121.7 | 14.27% | 2007M07 | 142.5 | 29.31%
2007M08 | 122.2 | 14.74% | 2007M08 | 142.4 | 29.22%
2007M09 | 122.7 | 15.21% | 2007M09 | 142.6 | 29.4%
2007M10 | 122.8 | 15.31% | 2007M10 | 142.7 | 29.49%
Contract Commencement
Contract Completion

## Project Start
Contract | Margin
5000000 | 750000
Costs
4250000
Labour | Increase Index | Cost Month 9
2125000 | 1.0604 | 2253435
Materials
2125000 | 1.098 | 2333250
4586685
CPA Value |  | 336685
Recoverable
5000000 | 1.0272 | 5136150
CPA Value |  | 136150
Loss to Contractor |  | 200535

## Costs over Time
t value | S-Curve | EO Month | Work Value | Value of IPC | Work Executed at end of Month | Work Cost (Base Date Value) | Material Index | Labour Index | Work Cost (at IPC Date) | CPI | IPC adjusted at CPI | Projected Margin | Actual Margin | Projected % Margin | Actual % Margin
-6 | 0.013488 | 0 |  |  |  |  | 9.8% | 6.044% |  | 2.723%
-5.5 | 0.018126 | 1 | 90628.5086 | 90628.5086 | 77034.2323 | 77034.2323 | 10.34% | 6.659% | 83583.6954 | 2.817% | 93181.4243 | 13594.2763 | 9597.7289 | 15% | 10.3%
-5 | 0.024321 | 2 | 121606.9418 | 30978.4332 | 26331.6682 | 103365.9005 | 11.16% | 7.275% | 28758.9592 | 3.005% | 31909.2406 | 4646.765 | 3150.2814 | 15% | 9.873%
-4.5 | 0.032569 | 3 | 162842.7739 | 41235.8321 | 35050.4573 | 138416.3578 | 12.07% | 7.89% | 38548.3675 | 3.099% | 42513.5621 | 6185.3748 | 3965.1946 | 15% | 9.327%
-4 | 0.043495 | 4 | 217473.067 | 54630.2931 | 46435.7491 | 184852.107 | 11.8% | 8.506% | 51149.5834 | 2.254% | 55861.3983 | 8194.544 | 4711.8149 | 15% | 8.435%
-3.5 | 0.057879 | 5 | 289396.4031 | 71923.336 | 61134.8356 | 245986.9426 | 11.62% | 9.121% | 67473.5025 | 3.099% | 74151.9465 | 10788.5004 | 6678.4439 | 15% | 9.006%
-3 | 0.076662 | 6 | 383309.3339 | 93912.9308 | 79825.9912 | 325812.9338 | 11.34% | 9.737% | 88239.6515 | 3.38% | 97087.4524 | 14086.9396 | 8847.8009 | 15% | 9.113%
-2.5 | 0.10092 | 7 | 504623.4539 | 121314.12 | 103117.002 | 428929.9358 | 11.62% | 10.35% | 114443.2659 | 3.85% | 125984.4289 | 18197.118 | 11541.163 | 15% | 9.161%
-2 | 0.13184 | 8 | 659175.4588 | 154552.0049 | 131369.2041 | 560299.14 | 11.98% | 10.97% | 146441.406 | 4.225% | 161082.3713 | 23182.8007 | 14640.9653 | 15% | 9.089%
-1.5 | 0.17053 | 9 | 852630.3152 | 193454.8565 | 164436.628 | 724735.768 | 12.25% | 11.58% | 184032.6343 | 4.507% | 202173.9486 | 29018.2285 | 18141.3143 | 15% | 8.973%
-1 | 0.2179 | 10 | 1089505.5857 | 236875.2704 | 201343.9799 | 926079.7478 | 12.52% | 11.63% | 225654.5697 | 4.507% | 247551.3389 | 35531.2906 | 21896.7693 | 15% | 8.845%
-0.5 | 0.27437 | 11 | 1371848.3921 | 282342.8064 | 239991.3855 | 1166071.1333 | 12.52% | 11.67% | 269018.686 | 4.977% | 296393.6691 | 42351.421 | 27374.9831 | 15% | 9.236%
0 | 0.33956 | 12 | 1697792.8693 | 325944.4772 | 277052.8056 | 1443123.9389 | 12.89% | 11.71% | 311123.6951 | 5.822% | 344919.6486 | 48891.6716 | 33795.9535 | 15% | 9.798%
0.5 | 0.41209 | 13 | 2060465.2245 | 362672.3553 | 308271.502 | 1751395.4408 | 13.97% | 11.75% | 347924.6665 | 5.915% | 384126.2129 | 54400.8533 | 36201.5464 | 15% | 9.424%
1 | 0.48957 | 14 | 2447832.6807 | 387367.4562 | 329262.3377 | 2080657.7786 | 14.79% | 11.79% | 373029.2002 | 5.728% | 409554.7001 | 58105.1184 | 36525.5 | 15% | 8.918%
1.5 | 0.56878 | 15 | 2843915.6923 | 396083.0117 | 336670.5599 | 2417328.3385 | 14.97% | 11.84% | 381798.3114 | 5.634% | 418397.5475 | 59412.4517 | 36599.2361 | 15% | 8.747%
2 | 0.64625 | 16 | 3231250.7468 | 387335.0544 | 329234.7962 | 2746563.1347 | 15.88% | 11.88% | 374928.7438 | 5.352% | 408065.663 | 58100.2582 | 33136.9191 | 15% | 8.12%
2.5 | 0.71877 | 17 | 3593863.7271 | 362612.9803 | 308221.0333 | 3054784.168 | 17.42% | 11.92% | 353440.5811 | 6.479% | 386106.2156 | 54391.947 | 32665.6346 | 15% | 8.46%
3 | 0.78395 | 18 | 3919730.8841 | 325867.157 | 276987.0835 | 3331771.2515 | 18.87% | 11.96% | 319693.1749 | 6.948% | 348509.5698 | 48880.0736 | 28816.3949 | 15% | 8.268%
3.5 | 0.8404 | 19 | 4201988.3832 | 282257.4991 | 239918.8742 | 3571690.1257 | 20.69% | 12% | 279137.2283 | 7.793% | 304255.0319 | 42338.6249 | 25117.8036 | 15% | 8.256%
4 | 0.88776 | 20 | 4438778.9583 | 236790.5752 | 201271.9889 | 3772962.1146 | 22.23% | 12.05% | 235767.625 | 8.263% | 256356.3692 | 35518.5863 | 20588.7442 | 15% | 8.031%
4.5 | 0.92643 | 21 | 4632155.7609 | 193376.8025 | 164370.2822 | 3937332.3967 | 22.14% | 12.09% | 192501.3174 | 8.545% | 209900.0786 | 29006.5204 | 17398.7613 | 15% | 8.289%
5 | 0.95733 | 22 | 4786639.6689 | 154483.908 | 131311.3218 | 4068643.7186 | 22.6% | 12.44% | 154315.0892 | 8.92% | 168264.1628 | 23172.5862 | 13949.0736 | 15% | 8.29%
5.5 | 0.98158 | 23 | 4907896.7661 | 121257.0972 | 103068.5326 | 4171712.2512 | 23.59% | 12.8% | 121821.6391 | 9.671% | 132984.3094 | 18188.5646 | 11162.6704 | 15% | 8.394%
6 | 1.0004 | 24 | 5001763.3972 | 93866.6311 | 79786.6364 | 4251498.8876 | 24.05% | 13.15% | 94626.0407 | 10.05% | 103297.3631 | 14079.9947 | 8671.3224 | 15% | 8.395%
|  |  |  | 5001763.3972 | 4251498.8876 |  |  |  | 4837451.6338 |  | 5302627.6535 | 750264.5096 | 465176.0197 | 15% | 8.773%
[5 empty] | 750264.5096 | [5 empty] | 465176.0197
285088.4899
Anticipated Margin
Actual Margin